## Sheet1
Question | Person | 2/27/2019: 6pm | 3/2/2019: 12pm | 3/3/2019: 10pm | 3/4/2019: 12pm | 3/6/2019: 12pm | 3/8/2019: 4pm | 3/9/2019: 12pm | 3/10/2019: 10pm | 3/11/2019: 6pm | 3/13/2019: 6pm
What did you complete since last meeting? | Gavin | First sprint meeting. Completed organizational tasks with the team | Initial set up of remote google firebase
| Joe | No prior meeting, but I helped the team create the requirements and user stories and storyboards | I created maze concept art for level 2
| Sinead | Level user stories, scenarios, and issues | Began working on the "about" and "help" pages and linking the to the main menu via an image button
| Austen | Completed work on sprite animations for the game | Continued work on sprites and sprite animations
What will you accomplish before the next meeting? | Gavin | Will look into how to use google firebase to prepare for issues incoming with sprint one. | Connecting this with an example app
| Joe | I will create mazes for the levels | I will work on my assigned issues
| Sinead | Start building pages for helping the user understand and game and learning about the team | Hopefully have nicer and neater UI versions of the linked pages
| Austen | I will continue working on sprites as well as the rest of the assigned issues in github | Continue sprite work as well as button design for the game
Do you have anything that's getting in the way of doing your work? | Gavin | Currently lacking the knowledge for database implementations with google firebase. | Various versioning issues and compiling on android studio is proving difficult for now
| Joe | Midterms for other classes | Midterms for other classes
| Sinead | Not knowing how to link activities | Not having a standard set of icons or images to use throughout the pages to keep consistent
| Austen | Nothing is currently getting in the way of my work | Nothing is currently getting in the way of my work
What insights have you made? | Gavin | Better understanding of sprint schedule and assigned responsibilities. | Currently using the 20 SDK for the emulator
| Joe | The collaboration will be key for things to work out efficiently | I have realized that compromise will be a necessary but challenging part of the project
| Sinead | We have an abundance of user stories, so each sprint will require much more work than we first anticipated | Linking activities through intents
| Austen | I learned how to use the software to make and animate sprites | I have learned how to improve the quality of sprite animation
Do any changes to the project need to be made as a result of your work? | Gavin | Not currently | Too early to determine
| Joe | No | No
| Sinead | Not yet | Not yet
| Austen | No changes need to be made to the current plan or the project | No changes need to be made to the current plan for the project