## Sheet1
Question | Person | 2/27/2019: 6pm | 3/2/2019: 12pm | 3/3/2019: 10pm | 3/4/2019: 12pm | 3/6/2019: 12pm | 3/8/2019: 4pm | 3/9/2019: 12pm | 3/10/2019: 10pm | 3/11/2019: 6pm | 3/13/2019: 6pm
What did you complete since last meeting? | Gavin | First sprint meeting. Completed organizational tasks with the team | Initial set up of remote google firebase | Successfully connected the application to Google firebase. Utilizing the following set up for the andrio studio project: Download android studio v3.3.1 for windows from chrome using API 20:Andriod 4.4W (kitkat wear) for project API using Nexus 5x API with Nougat 24 OS for emulated device. Completed basic design for security question update page. Completed back end for security question page however does not consider user account or database, will have to e updated for password verification and to actually update database
| Joe | No prior meeting, but I helped the team create the requirements and user stories and storyboards | I created maze concept art for level 2 | I created maze concept art for level 3
| Sinead | Level user stories, scenarios, and issues | Began working on the "about" and "help" pages and linking the to the main menu via an image button | No significant progress
| Austen | Completed work on sprite animations for the game | Continued work on sprites and sprite animations | Continued work on sprites for the game
What will you accomplish before the next meeting? | Gavin | Will look into how to use google firebase to prepare for issues incoming with sprint one. | Connecting this with an example app | Try to connect the submission of a security question with Google firebase
| Joe | I will create mazes for the levels | I will work on my assigned issues | I will work on my assigned issues
| Sinead | Start building pages for helping the user understand and game and learning about the team | Hopefully have nicer and neater UI versions of the linked pages | Hopefully have the right design down for the help and about pages
| Austen | I will continue working on sprites as well as the rest of the assigned issues in github | Continue sprite work as well as button design for the game | Continue to work on sprite animations and button code for the game
Do you have anything that's getting in the way of doing your work? | Gavin | Currently lacking the knowledge for database implementations with google firebase. | Various versioning issues and compiling on android studio is proving difficult for now | Not currently
| Joe | Midterms for other classes | Midterms for other classes | Chores for spring break
| Sinead | Not knowing how to link activities | Not having a standard set of icons or images to use throughout the pages to keep consistent | Travel and Time Difference
| Austen | Nothing is currently getting in the way of my work | Nothing is currently getting in the way of my work | Nothing is currently getting in the way of my work
What insights have you made? | Gavin | Better understanding of sprint schedule and assigned responsibilities. | Currently using the 20 SDK for the emulator | Installing Android studio from certain rowsers has proven to be problematic. So far google chrome has been issue free.
| Joe | The collaboration will be key for things to work out efficiently | I have realized that compromise will be a necessary but challenging part of the project | documentation is tricky to master
| Sinead | We have an abundance of user stories, so each sprint will require much more work than we first anticipated | Linking activities through intents | It's easier to get work done when you can communcate with your team
| Austen | I learned how to use the software to make and animate sprites | I have learned how to improve the quality of sprite animation | Continue learning how to utilize new animation techniques
Do any changes to the project need to be made as a result of your work? | Gavin | Not currently | Too early to determine | Versions od IDE, project, and emulator sohuld be consistent while in the rapid prototyping phase.
| Joe | No | No | No
| Sinead | Not yet | Not yet | Not yet
| Austen | No changes need to be made to the current plan or the project | No changes need to be made to the current plan for the project | No changes need to be made to the project currently